xLoop Digital

Creatio and Pipedrive Partnership

Marketing Plan

Prepared for Huzaifa Valika, VP Enterprise Sales  ·  Prepared by Sana Qazi, Marketing  ·  Thu 29 Oct 2026

The short version - Sell the outcome, not the badge. Buyers care that someone can get a CRM live, move their data in cleanly, connect it to their other systems and put AI on top. That is work xLoop already does: data migration, integration and AI agents. - Two partners, two buyers. Creatio is for mid-market and enterprise firms in regulated industries, especially banking. Pipedrive is for growth-stage and SMB sales teams. We keep the two stories separate. - Where the return is: partner directories, the vendors’ own co-marketing, and direct outreach by sales. No paid ads and no large website launch. - Timeline: confirm the basics this week, launch Mon 2 Nov to Fri 13 Nov 2026, then a six-week demand push to Fri 18 Dec 2026.

# 1. Positioning

One line (internal): xLoop implements Creatio and Pipedrive, migrates your data into them, connects them to the rest of your stack, and adds AI that actually gets used.

|  | Creatio | Pipedrive |
| --- | --- | --- |
| Buyer | CIO, CTO, Head of Digital, Head of Operations at banks, insurers, energy and public sector | Founder, Head of Sales, Sales Ops at growth-stage firms |
| Their problem, in their words | “Our CRM is old, slow to change, and IT is the bottleneck.” “We want AI in our workflows, not another pilot.” | “Our pipeline lives in spreadsheets.” “We bought a CRM and nobody uses it.” |
| What we lead with | Implementation, migration from a legacy CRM, integration with core systems, AI agents inside workflows | Fast setup, migration from spreadsheets or an old CRM, integrations, training so the team adopts it |
| Our proof today | Data migration, integration and AI agent delivery. No Creatio project yet | Same. No Pipedrive project yet |
| Sales cycle | Months, several stakeholders | Weeks |
| Fit with our buyer profiles | Strong: AI Transformation Sponsor and Data Modernization Owner | A new segment outside our current profiles |

Words to avoid: “reseller”, “official partner of” as a headline, “certified experts” until our people are certified, and any partner tier we do not yet hold.

# 2. Before anything goes public (this week, by Fri 30 Oct 2026)

Nothing is published until these are confirmed in writing.

| To confirm | Owner |
| --- | --- |
| Signed agreements for both, and our tier in each program | Huzaifa |
| Each vendor’s partner brand guidelines, logo files, and whether they must approve our announcement wording | Huzaifa, then Sana |
| Name of our partner manager and channel marketing contact at each vendor | Huzaifa |
| Are we allowed to resell licenses, or implement only? This changes the CTA and the website copy | Huzaifa |
| How many xLoop people are trained or certified on each platform, and by when | Huzaifa with delivery |
| Any Creatio or Pipedrive work already done, even an internal or demo build we can show | Huzaifa with delivery |
| A named owner for incoming partner leads, with a reply time | Huzaifa |
| Are we ready to sell and support Pipedrive seats at SMB prices? | Huzaifa with leadership |

# 3. Phase 1: Launch (Mon 2 Nov to Fri 13 Nov 2026)

## 3.1 Partner directories (highest return, no cost)

- Complete our profile in the Creatio partner catalog and the Pipedrive partner directory: services, industries, regions (Pakistan, UAE, Saudi Arabia, USA, Europe), languages and contact.

- Buyers looking for an implementer search here first, and the vendors route leads from here.

- Owner: Sana writes, Huzaifa submits. Effort: one day.

## 3.2 Vendor co-marketing (ask early)

Pipedrive offers marketing development funds (MDF) and channel marketing support. Creatio runs co-marketing with its partners. Questions for the first call with each partner manager:

- Will they share our announcement on their channels?

- What MDF or co-marketing budget can we claim, and for what activities?

- Can they refer leads to us in our regions? Pakistan and the GCC have few partners.

- Do they have ready-made campaign kits (emails, one-pagers, demo scripts) we can co-brand?

- Owner: Huzaifa.

## 3.3 Website (small and fast)

- Add the Creatio and Pipedrive logos to the partners strip, beside AWS, Microsoft, Snowflake, Databricks and Salesforce.

- Build one page, “CRM Implementation and Integration”, under the Digital Transformation cluster, with a Creatio section and a Pipedrive section. One page, not two, until demand justifies more.

  - It targets searches such as “Creatio implementation partner UAE” and “Pipedrive partner Pakistan”. Volumes are small but buyer intent is high. We check volumes before writing.

  - The CTA names what the buyer gets, for example “Get your CRM migration plan”, and only if delivery agrees to produce one after a first call.

- Every social post and email links to this page, never the homepage.

- Owners: Sana (copy), Omais and Rafay (design), production developers (build). Effort: about two weeks end to end.

## 3.4 LinkedIn announcement

- Company page: one carousel. Slide 1 states the buyer’s problem, not “We’re proud to announce”. Then what we now deliver with Creatio and Pipedrive, then one CTA to the new page.

- Huzaifa’s own post: why we chose these two platforms and who each is for.

- CEO and COO reshare with one line each.

- Tag both vendors so they can reshare.

- Owners: Sana (copy), Omais (carousel). Needs two working days’ notice.

# 4. Phase 2: Demand push (Mon 16 Nov to Fri 18 Dec 2026)

## 4.1 Sales enablement

This is the core of the plan, because our sales motion is direct outreach and partner-led.

| Asset | Used for | Owner |
| --- | --- | --- |
| Creatio one-pager: problem, what we do, how we engage, next step | Enterprise outreach | Sana and Omais |
| Pipedrive one-pager with a fixed-scope setup package | SMB outreach | Sana and Huzaifa (scope and price) |
| Comparison sheet: Creatio vs Salesforce and Dynamics; Pipedrive vs HubSpot and Zoho; when to recommend which | Sales calls | Irfan (technical check) and Sana |
| Three-email outreach sequence per partner | Sales team | Sana |
| Discovery call script and qualifying questions | Sales team | Huzaifa |
| Demo environment (both vendors provide one to partners) | Sales demos | Delivery |

## 4.2 Who to target first

- Existing xLoop clients. The warmest and fastest: anyone on an old CRM or spreadsheets, or asking for AI in sales or service.

- Banks and financial services in Pakistan and the GCC for Creatio. It is Creatio’s strongest vertical, and ours.

- Growth-stage companies in Pakistan and the UAE for Pipedrive.

- Leads referred by the vendors’ partner teams.

## 4.3 Content, inside the existing Q2 calendar

| Date | Piece | Lead |
| --- | --- | --- |
| Mon 23 Nov 2026 | Blog: “Creatio vs Salesforce for banks: how to choose” | Sana, Irfan review |
| Mon 7 Dec 2026 | Blog: “Moving from spreadsheets to Pipedrive: a migration checklist” | Sana, Irfan review |
| Every other week | LinkedIn: AI agents inside your CRM workflows (Creatio) | Irfan |
| Every other week | LinkedIn: why CRM rollouts fail, and it is adoption, not software (Pipedrive) | Huzaifa |
| Every other week | LinkedIn: migrating CRM data without losing history | Irfan |

Posts are carousels or short videos, and every one links to the CRM page.

## 4.4 Optional, only if a vendor offers it

- A joint webinar or roundtable run by the vendor.

- A joint press release, or a listing in the vendor’s partner news.

# 5. How we measure it

Reported monthly, on one slide for the CEO. Targets marked TBD are for Huzaifa to set.

| Metric | Target |
| --- | --- |
| Directory profiles live | Both by Fri 13 Nov 2026 |
| Leads referred by the vendors | TBD |
| Outreach meetings booked, per partner | TBD |
| Opportunities registered with each vendor | TBD |
| Pipeline value | TBD |
| Pipedrive seats sold (31 to 50 committed in our application for year one) | On track to 31 |
| Marketing development funds claimed | Any |
| Visits and form fills on the CRM page | Baseline from launch |

# 6. Risks

- No CRM delivery proof yet. Until the first project ships, we sell on related proof: data migration, integration and AI agents. The first Creatio and first Pipedrive projects should become anonymous case studies as soon as possible.

- Pipedrive pulls toward SMB. A different buyer, price point and support load. It stays off the homepage and out of the enterprise story.

- A site defect (the brand name repeats in every page title) will hold back the new page in search. It should be fixed before launch.

- Marketing capacity is limited. This plan is sized to the current team. Anything added means something else comes out.

# 7. Next steps

- Huzaifa confirms the items in section 2: agreements, tier, guidelines, resale rights, certifications, lead owner.

- Huzaifa books the first co-marketing call with each partner manager.

- Sana drafts both directory profiles once our tier is confirmed.

- Sana briefs Omais on the announcement carousel.

- Sana writes the CRM page copy; production schedules the build.

- Huzaifa and Sana agree the KPI targets.

- Sana adds the two blogs and three posts to the Q2 calendar.

## Sources

- Creatio: partner benefits

- Creatio: partner-driven strategy

- Pipedrive: solution provider partnership

- Pipedrive program announcement, BusinessWire, June 2025